## Plan
Migration plan
1. Prepare
what |  | who | status | when | comments
1.1 | plan: accounts, machines etc. | rhanusch | done | 2013-01-02
1.2 | install 64b OS | SOS | done | 2013-01-15
1.3 | partitions, accounts, home and data disks | SOS | done | 2013-01-15
1.4 | cross-account ssh access | SOS | done | 2013-01-15
1.5 | enable ssh access for DHA/opslogs | SOS | done | 2013-02 | automatic: copy of ssh keys from dfo to muc blades
1.6 | enable ssh access for ASG (preimg) | SOS | done | 2013-02 | automatic: copy of ssh keys from dfo to muc blades
1.7 | 64b VLT+DFS | SOS+DFI | done | 2013-01-15
1.8 | 64b pipelines | SOS+DFI | done | 2013-01-18
2. Cleanup data, logs, tools
what |  | who | status | when | comments
2.1 | update .dfosrc | QCG |  |  | only DFO_MACHINE; use .dfosrc_muc
2.2 | prepare dfo directories for migration | QCG |  |  | good occasion to remove obsolete information; use muc_migrate | Details
2.3 | decide: cp or sync dfo directories to new machines | rhanusch, QCG, SOS |  |  | we do it ourselves: muc_migrate
2.4 | call muc_migrate to learn about, and start migration (setup phase) | QCG
3. Migrate data, directories, tools
what |  | who | status | when | comments
3.1 | Call muc_migrate for full data migration | QCG |  |  |  | Details
3.2 | Do a scp for all non-standard directories | QCG |  |  | This step needs to be done manually by the QC scientists.
4. Commissioning phase for operations: test dfos on new, do dfos on old hardware
what |  | who | status | when | comments
4.1 | Test access: databases, NGAS; read, write | QCG, |  |  | see migration plan
4.2 | Test firefox; check compatibility--> NO! | QCG
4.2 | Test dfs tools | QCG
4.3 | Test pipelines | QCG
4.4 | Test dfos tools | QCG
4.5 | Let selected processes run on new hardware | QCG
4.6 | make calChecker operational | QCG
| call trendPlotter; JOBS_HEALTH etc. | QCG
5. Operations: switch dfos from old to new hardware
what |  | who | status | when | comments
5.1 | Make sure to have non-permanent data ready on new hardware | QCG |  |  | use muc_migrate for VCAL, PREVIOUS etc.
5.2 | switch calChecker to new | QCG |  |  | do it on a Monday
5.3 | switch autoDaily to new | QCG |  |  | do it on a Monday
5.4 | switch trendPlotter to new | QCG |  |  | do it on a Monday
make sure to not change $TMP_DIR etc. at that point (otherwise nightmare switching forth and back); do it later
transition: call muc_migrate -I every day
transition: work one day behind autoDaily
6. Backup plan
what |  | who | status | when | comments
6.1 | Agree on backup plan | QCG+SOS | done | 2013-02

## Directories
This is an overview of all dfos directories. The second column has an indication of what kind of actions they will need for the migration. Details are provided in the following sheets.
Any additional, non-standard directories you might have are not covered by this plan and should be managed by yourself.
directory | where? | actions (CLN: cleanup; MIG: migrate; FILL: fill with new content)
$TMP_DIR |  | no content to be migrated; structure to be created, script! ($TMP_DIR/CALCHECK etc.)
$DFO_CONFIG_DIR | $HOME | MIG
$DFO_PROC_DIR | $HOME | MIG
$DFO_JOB_DIR | $HOME | CLN; MIG; FILL
$DFO_TREND_DIR | $HOME or $DATA | CLN (reports/trend_report*); MIG; FILL (statFiles)
$DFO_MON_DIR |  | CLN; MIG (FINISHED); FILL (current)
$DFO_BIN_DIR |  | MIG
$DFO_DOC_DIR |  | MIG
$DFO_GUI_DIR |  | CLN; MIG; FILL
$DFO_INSTALL_DIR |  | CLN (for obsolete tools); MIG
backup directory |  | MIG; FILL
$DFO_RAW_DIR |  | CLN; MIG; FILL
$DFO_SCI_DIR |  | MIG (should have historical subdirs and hdr only!)
$DFO_SRV_DIR |  | MIG (should have historical subdirs and hdr only!)
$DFO_CAL_DIR |  | MIG; FILL
$DFO_HDR_DIR |  | MIG; FILL
$DFO_LST_DIR |  | MIG; FILL
$DFO_LOG_DIR |  | MIG; FILL
$DFO_PLT_DIR |  | MIG; FILL
$DFO_OPS_DIR |  | none (to be auto-filled and cross-mounted on new machines)
$DFS_LOG |  | CLN; FILL
$DFS_REDBLOCK |  | remove
$DFS_PRODUCT |  | CLN (for obsolete date directories); MIG; FILL
$MID_WORK |  | CLN
$DFS_DO_DB |  | clean entirely; subdirectories are required by DFS (?) but should be emtpy, no fits files!
config.processAB: WORK_AREA |  | clean entirely
$BQSROOT/condor |  | CLN (for obsolete date directories); MIG; FILL
why?
$HOME is backed up
$DATA only from time to time, no fits

## Cleanup
CLEANUP: Before migration, we want to clean up obsolete information. This is mostly left-behind stuff from incomplete reprocessing, calSelector calls etc. It does not catch immediate attention. But over the years it piles up and may cause unexpected damage. For instance, it may prevent quick action for the QC shift leader, simply because of confusion.
So please clean up the following directories, before further action. The content to be removed is indicated in the second colunm. This list is probably incomplete.
Action=CLN: | standard clean procedure; remove: all content with outdated DATE information
*199* ¦ *200* *2010* *2011* *2012* (provided you are done with 2012)
Checklist:
directory | check | actions
$DFO_JOB_DIR | done? | CLN
$DFO_TREND_DIR | done? | clean reports/trend_report* only
$DFO_MON_DIR | done? | CLN; make sure to *NOT* clean FINISHED!
$DFO_GUI_DIR | done? | CLN
$DFO_INSTALL_DIR | done? | clean for obsolete tool directories
$DFO_RAW_DIR | done? | CLN
$DFO_SCI_DIR | done? | should have historical subdirs and hdr only, do *NOT* clean those; any other content should be cleaned
$DFO_SRV_DIR | done? | should have FINISHED only, do *NOT* clean this one
$DFS_LOG | done? | CLN
$DFS_REDBLOCK | done? | remove entirely
$DFS_PRODUCT | done? | clean for obsolete DATE directories: e.g. rm -r */200*
$MID_WORK | done? | CLN entirely
$DFS_DO_DB | done? | clean entirely; subdirectories are required by DFS (?) but should be emtpy, no fits files!
config.processAB: WORK_AREA | done? | clean entirely
$BQSROOT/condor | done? | clean for obsolete DATE directories: e.g. rm -r *200*

## Migrate
MIGRATE: the content is scopied to the corresponding directory on the new machine. TBD: should this become a snapshot or a sync?
A sync makes sense only if it can be sustained for a transition period as along as several weeks. Issues are performance, and volume. If a sync is possible, there is no issue with the last step, FILL. Then the sync is turned off at some point, and we run all operations on the new machines only. If sync is not possible, we need to fill non-permanent information from the old to the new machines in order to switch operations.
Checklist:
directory | check | actions
$TMP_DIR | done? | no content to be migrated; structure to be created, script! ($TMP_DIR/CALCHECK etc.)
$DFO_CONFIG_DIR | done? | MIG
$DFO_PROC_DIR | done? | MIG
$DFO_JOB_DIR | done? | MIG, FILL
$DFO_TREND_DIR | done? | MIG; FILL (statFiles)
$DFO_MON_DIR | done? | MIG (FINISHED); FILL (current)
$DFO_BIN_DIR | done? | MIG
$DFO_DOC_DIR | done? | MIG
$DFO_GUI_DIR | done? | MIG, FILL
$DFO_INSTALL_DIR | done? | MIG
backup directory | done? | MIG, FILL
$DFO_RAW_DIR | done? | MIG; FILL
$DFO_SCI_DIR | done? | MIG (should have historical subdirs and hdr only!)
$DFO_SRV_DIR | done? | MIG (should have historical subdirs and hdr only!)
$DFO_CAL_DIR | done? | MIG; FILL
$DFO_HDR_DIR | done? | MIG; FILL
$DFO_LST_DIR | done? | MIG; FILL
$DFO_LOG_DIR | done? | MIG; FILL
$DFO_PLT_DIR | done? | MIG; FILL
$DFO_OPS_DIR | done? | none (to be auto-filled and cross-mounted on new machines)
$DFS_LOG | done? | FILL
$DFS_PRODUCT | done? | MIG; FILL
$MID_WORK | done? | MIG (empty)
$DFS_DO_DB | done? | subdirectories are required by DFS (?) but should be emtpy, no fits files!
$BQSROOT/condor | done? | MIG; FILL