| LISA Local Organizing Committee (LOC) Checklist and Timeline (Revised by LISA V LOC, March 2005) |  |  |
| --- | --- | --- |
| ## Task | ## Timeline | Comments |
| Decide conference site | 18 months before meeting | Done by POC together with LOC |
| Decide conference dates | 18 months | Done by LOC together with POC |
| Secure meeting site (auditorium and adjacent rooms, technical and administrative staff to help with preparations and during the conference, logistical support from institute etc.) | 18 months | Avoid in-house conflicts! Make sure rooms, facilities, and support staff are available exclusively for LISA meeting |
| Contact nearby hotels and dormitories for (reduced?) rates | 18 months |  |
| Post and mail preliminary announcement | 15 months | Sent by POC, content in cooperation with LOC. For distribution, use usual mailing lists (Astrolib, PAMnet, PAM-APF, EGAL, etc.), post on conference website (if already available) and get lists of previous participants from proceedings |
| Design and print conference poster | 15 months | Can be outsourced if no in-house expertise |
| Contact possible local sponsors | 12 months | In cooperation with FOL to avoid contacting sponsors twice |
| Set up bank account and procedures to handle incoming (from sponsors) and outgoing (to FOL grantees, for rentals etc.) money | 12 months | LOC is largely in charge of finding procedures for transfer of funds from funding agencies, SOC and/or FOL. |
| Set up conference web site; develop pre-registration form | 12 months |  |
| Post and mail 1st announcement | 12 months | Content in cooperation with SOC. For distribution, use usual mailing lists (Astrolib, PAMnet, PAM-APF, EGAL, etc.), post on conference website and get lists of previous participants from proceedings |
| Investigate suitable sites for conference banquet | 12 months | Charged seperately, not from registration fee |
| Contact local bus companies in case transportation between conference site and lodging is necessary | 9 months | Bus transport may also be needed for social events and field trips. In cooperation with SOC and FOL |
| Investigate options for post-conference field trips | 9 months | Charged separately, not from registration fee. In cooperation with SOC and FOL |
| Prepare input for 2nd announcement (info about conference facilities, technical equipment lodging, social events, field trips, local transportation) | 7 months |  |
| Post and mail 2nd announcement | 6 months | Content in cooperation with SOC |
| Consider items that may be included in the Welcome Bag | 3 months | Goodies from local sponsors or host institute |
| Prepare and print program booklet | 1 month |  |
| Prepare final list of conference registrants | a few weeks | Check that all fees have been paid |
| Prepare final lists for conference dinner, social events, field trips | a few weeks |  |
| Give final numbers to caterer, restaurant, field trip contacts | a few weeks |  |
| Give final list of required equipment to local technical staff | a few weeks |  |
| Arrange for photographer for conference group photo and photos taken during the sessions, coffee breaks, conference dinner etc. | a few weeks | Institute staff or hired photographer. Note: Amateur pixs are nice, but a professional photographer assures quality photos |
| Organize registration process: - Prepare "Welcome Bag“: Registration packet including final program booklet, name tags, local tourist information, maps, suggestions for nearby restaurants, etc - Make arrangements for grant money if it is to be distributed in registration packet - Organize personnel to be available throughout the conference at registration desk | a few weeks |  |
| Finalize equipment and arrangements for poster paper display | 1 week |  |
| Get cash for grant money, place in envelopes, prepare to distribute; prepare receipts for signing | 1 week |  |
| Set up easels or bulletin boards for posters | 1 day |  |
| Review and test equipment and technology with local staff | 1 day |  |
| Post orientation help inside conference building (arrows, signs, etc) | 1 day |  |
| Check in registrants on list | Registration process | Keep records of unexpected guests, no-shows |
| Collect any unpaid fees, e.g. dinner or field trip costs | Registration process |  |
| Hand out grant money to FOL recipients | Registration process | Get signed receipt Note: pay lodging fees for FOL recipients as required by dorm/hostel |
| Arrange and announce time/location for group photo | During meeting |  |
| Make other announcements as needed | During meeting |  |
| Be prepared to answer questions and solve problems regarding: - Technology and equipment - Catering and conference social events - Lodging and transportation issues | During meeting |  |
| Arrange for water for speakers/panels | During meeting |  |
| Monitor clean-up | After meeting |  |
| Monitor return of any rented equipment (e.g. easels) | After meeting |  |
| Monitor payment of bills (caterer, restaurant, field trip, printing, etc) | After meeting |  |
| Arrange for production of group photo (and any other photos) - Mail copy of photo to each attendee - Post photo on Web site - Send photo to proceedings editors for inclusion in published volume | After meeting |  |
| Make final statement of budget; keep remaining funds in secure account to transfer them to next FOL | After meeting |  |