| LISA Local Organizing Committee (LOC) Checklist and Timeline (Revised by LISA V LOC, March 2005) |
| --- |
| Task | Timeline | Comments |
| Decide conference site | 18 months before meeting | Done by POC together with LOC |
| Decide conference dates | 18 months | Done by LOC together with POC |
| Secure meeting site (auditorium and adjacent rooms, technical and administrative staff to help with preparations and during the conference, logistical support from institute etc.) | 18 months | Avoid in-house conflicts! Make sure rooms, facilities, and support staff are available exclusively for LISA meeting |
| Contact nearby hotels and dormitories for (reduced?) rates | 18 months |  |
| Post and mail preliminary announcement | 15 months | Sent by POC, content in cooperation with LOC. For distribution, use usual mailing lists (Astrolib, PAMnet, PAM-APF, EGAL, etc.), post on conference website (if already available) and get lists of previous participants from proceedings |
| Design and print conference poster | 15 months | Can be outsourced if no in-house expertise |
| Contact possible local sponsors | 12 months | In cooperation with FOL to avoid contacting sponsors twice |
| Set up bank account and procedures to handle incoming (from sponsors) and outgoing (to FOL grantees, for rentals etc.) money | 12 months | LOC is largely in charge of finding procedures for transfer of funds from funding agencies, SOC and/or FOL. |
| Set up conference web site; develop pre-registration form | 12 months |  |
| Post and mail 1st announcement | 12 months | Content in cooperation with SOC. For distribution, use usual mailing lists (Astrolib, PAMnet, PAM-APF, EGAL, etc.), post on conference website and get lists of previous participants from proceedings |
| Investigate suitable sites for conference banquet | 12 months | Charged seperately, not from registration fee |
| Contact local bus companies in case transportation between conference site and lodging is necessary | 9 months | Bus transport may also be needed for social events and field trips. In cooperation with SOC and FOL |
| Investigate options for post-conference field trips | 9 months | Charged separately, not from registration fee. In cooperation with SOC and FOL |
| Prepare input for 2nd announcement (info about conference facilities, technical equipment lodging, social events, field trips, local transportation) | 7 months |  |
| Post and mail 2nd announcement | 6 months | Content in cooperation with SOC |
| Consider items that may be included in the Welcome Bag | 3 months | Goodies from local sponsors or host institute |
| Prepare and print program booklet | 1 month |  |
| Prepare final list of conference registrants | a few weeks | Check that all fees have been paid |
| Prepare final lists for conference dinner, social events, field trips | a few weeks |  |
| Give final numbers to caterer, restaurant, field trip contacts | a few weeks |  |
| Give final list of required equipment to local technical staff | a few weeks |  |
| Arrange for photographer for conference group photo and photos taken during the sessions, coffee breaks, conference dinner etc. | a few weeks | Institute staff or hired photographer. Note: Amateur pixs are nice, but a professional photographer assures quality photos |
| Organize registration process: Prepare "Welcome Bag“: Registration packet including final program booklet, name tags, local tourist information, maps, suggestions for nearby restaurants, etc Make arrangements for grant money if it is to be distributed in registration packet Organize personnel to be available throughout the conference at registration desk | a few weeks |  |
| Finalize equipment and arrangements for poster paper display | 1 week |  |
| Get cash for grant money, place in envelopes, prepare to distribute; prepare receipts for signing | 1 week |  |
| Set up easels or bulletin boards for posters | 1 day |  |
| Review and test equipment and technology with local staff | 1 day |  |
| Post orientation help inside conference building (arrows, signs, etc) | 1 day |  |
| Check in registrants on list | Registration process | Keep records of unexpected guests, no-shows |
| Collect any unpaid fees, e.g. dinner or field trip costs | Registration process |  |
| Hand out grant money to FOL recipients | Registration process | Get signed receipt Note: pay lodging fees for FOL recipients as required by dorm/hostel |
| Arrange and announce time/location for group photo | During meeting |  |
| Make other announcements as needed | During meeting |  |
| Be prepared to answer questions and solve problems regarding: Technology and equipment Catering and conference social events Lodging and transportation issues | During meeting |  |
| Arrange for water for speakers/panels | During meeting |  |
| Monitor clean-up | After meeting |  |
| Monitor return of any rented equipment (e.g. easels) | After meeting |  |
| Monitor payment of bills (caterer, restaurant, field trip, printing, etc) | After meeting |  |
| Arrange for production of group photo (and any other photos) Mail copy of photo to each attendee Post photo on Web site Send photo to proceedings editors for inclusion in published volume | After meeting |  |
| Make final statement of budget; keep remaining funds in secure account to transfer them to next FOL | After meeting |  |