| ## LISA Scientific Organizing Committee (SOC) Checklist and Timeline |  |  |
| --- | --- | --- |
| ## Task | ## Timeline | ## Comments |
| Chair(s) solicit ideas for preliminary program | 9-10 months before meeting |  |
| Solicit quotes from publishers | 9-10 months |  |
| Coordinate with FOL re: funding requests / soliciting letters to sponsors | 9-10 months |  |
| Contact keynote and other invited speakers | 8 months |  |
| Set deadline for abstract submission | 7 months | ## Largely determined by LOC printing requirements (program booklet) |
| Prepare template for abstracts submission and make it available via conference web site | 7 months |  |
| Prepare 1st announcement and call for papers; mention deadline for abstracts submission | 7 months | ## Announcements are posted and mailed by LOC |
| Organize abstracts; 1st draft of program | 6 months |  |
| Solicit input from committee on 1st draft | 5 months | ## Chair(s) need to organize abstracts into coherent format |
| Finalize program, develop daily schedule & share with LOC & SOC committee members | 5 months | Chair(s) need to see draft copy of the program from LOC before going to press. Double check participant’s names, addresses and affiliations! |
| Send notices of accepted papers and posters to participants | 5 months | ## Coordinate efforts with FOL |
| Send notifications to contributors that were turned down | 5 months |  |
| Assign and contact Session Chairs | 3 months |  |
| Post and mail 2nd announcement | 3 months | ## Distributed by LOC |
| Finalize details regarding publisher; choose proceedings editors | 3 months | ## Analyze page costs, etc. and discuss allowable length of oral and poster paper presentations |
| Write instructions for authors and make them available through web site | 3 months |  |
| Set deadline for post-conference receipt of manuscripts for proceedings | 3 months | ## In coordination with publisher |
| Assign someone to set up a web photo gallery and transfer (copy) the website to ESO (“official” LISA website) | 1 month | ## Coordinate efforts with professional photographer |
| Review technical arrangements with LOC | Upon arrival at meeting site |  |
| Monitor all aspects of the meeting, make sure everything runs smoothly | During meeting | ## In cooperation with LOC |