	[image: image1.png]




ESO - EUROPEAN SOUTHERN OBSERVATORY


	EUROPEAN SOUTHERN OBSERVATORY
Organisation Européenne pour des Recherches Astronomiques dans l'Hémisphère Austral
Europäische Organisation für astronomische Forschung in der südlichen Hemisphäre


VERY LARGE TELESCOPE

PRIMET Test Plan

June 2013
Doc. No.: VLT-PLA-ESO-15700- XXX
Issue 1
Date:4/6/2013
Prepared:
 S.Leveque



Name



Date



Signature


Approved:





Name



Date



Signature


Released:





Name



Date



Signature

CHANGE RECORD

	Issue
	Date
	Affected Paragraphs(s)
	Reason/Initiation/Remarks

	1
	4/6/2013
	All
	First issue

	
	
	
	


TABLE OF CONTENTS

41
Scope

2
Reference document
4
3
Introduction
4
4
Overall schedule- Request for Paranal support
5
5
Availability
7
6
Task description
8


1 Scope

This document presents the activities related to PRIMET for the June2013 run, as well as the necessary support from Paranal.
2 Reference document

	Reference 
	Doc. number
	Issue
	Date
	Title

	RD 1
	
	
	
	

	
	
	
	
	


3 Introduction

The main objective is to calibrate PRIMET for the new A1 station as well as for the J2 station with the new STS-VCM.
This document, the schedule as well as additional procedures related to this run are located at
\\ads-fs1\Shared\TSD\PRIMA Metrology\15730 PRIMA Metrology\15730 Project docs-data package\AIV-COM
4 Overall schedule- Request for Paranal support
	Jun-13
	Tue
	Wed
	Thu
	Fri
	Sat
	Sun
	Mon
	Tue
	Wed
	Thu
	Fri
	Sat
	Sun
	Mon

	 Leveque
	18
	19
	20
	21
	22
	23
	24
	25
	26
	27
	28
	29
	30
	1

	Tunnel
	T
	VLTI
	 
	 
	 
	PRIMA
	 
	 
	 
	 
	 
	 
	 

	UT1
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	UT2
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	UT3
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	UT4
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	AT1
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	AT2
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	AT3
	 
	DF-A1
	X
	X
	
	
	DF-G2
	DF-A1
	 
	 
	 
	 
	 
	SF-D0

	AT4
	 
	
	DF-J2
	 
	X
	 X
	XM2 RR
	DF-G2
	DF-J2
	
	 
	 
	 
	SF-B2

	DL1
	U1
	U1
	U1
	U1
	U1
	U1
	 
	 
	 
	 
	 
	 
	 
	 

	DL2
	U2
	U2
	U2
	U2
	U2
	U2
	DF-G2
	 
	 
	 
	 
	 
	 
	 

	DL3
	U3
	U3
	U3
	U3
	U3
	U3
	 
	 
	 
	 
	 
	 
	 
	 

	DL4
	U4
	U4
	U4
	U4
	DF-J2
	U4
	DF-J2
	
	
	 
	 
	 
	 
	 

	DL5
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	DL6
	 
	DF-A1
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	VLTI lab
	 
	 
	?
	?
	?
	?
	 
	 
	 
	 
	 
	 
	 
	 

	DDL 1-3
	 
	 
	?
	?
	?
	?
	X
	X
	X
	 
	 
	 
	 
	 

	DDL 2-4
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	AT3-M2-RR
	 
	 
	 
	 
	
	 
	 X
	 
	 
	 
	 
	 
	 
	 

	AT4-M2-RR
	 
	 
	 
	 
	
	 X
	 
	 
	 
	 
	 
	 
	 
	 

	FSU/Marcel Alignment
	X
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 


	Date
	Activity
	responsible
	Request for Paranal support

	≤18/6
	FSU/Marcel Alignment


	
	Instrumentation (P.Bourget ?)

	19/6
	Arrival S.Leveque
	
	

	
	Move AT3-DF-A1
	
	Mechanical group

	
	Change AT3-DF ROC (afternoon)
	Leveque
	

	
	Move M12 (DF) A1-DL6
	
	VLTI (syst Eng ?)

	
	
	
	

	20/6
	Move AT4-DF-J2
	
	Mechanical group

	
	Change AT4-DF ROC
	Leveque
	

	
	PRIMET AT3 pupil tracker calibration Coude RR (day 1)
	Leveque
	

	
	
	
	

	21/6
	PRIMET AT3 pupil tracker calibration Coude RR (day 2)
	Leveque
	

	
	
	
	

	22/6
	Move M12 (DF) J2-DL4
	
	VLTI (syst Eng ?)

	
	PRIMET AT4 pupil tracker calibration Coude RR (day 1)
	Leveque
	

	
	
	
	

	23/6
	PRIMET AT4 pupil tracker calibration Coude RR (day 2). Morning only
	Leveque
	

	
	Move back M12 U4-DL4 (for night observation)
	
	VLTI (syst Eng ?)

	
	Install AT4-M2-RR (afternoon)
	
	POL

	
	Lift AT4-ROS to install RR-cover
	Leveque
	Mechanical group

	
	
	
	

	24/6
	Move AT3-DF-G2
	
	Mechanical group

	
	Change AT3-DF ROC 
	Leveque
	

	
	install RR-cover
	Leveque
	

	
	Install AT3-M2-RR
	
	POL

	
	Move M12 (DF) G2-DL2
	
	VLTI (syst Eng ?)

	
	Derotator test (standalone G2 day-time)
	Woillez
	

	
	
	
	

	
	Move M12 (DF) J2-DL4
	
	VLTI (syst Eng ?)

	
	PRIMET AT4 test on M2-RR (day)
	Leveque
	

	
	
	
	

	
	Start DDL1&3  laser replacement
	Leveque
	TBC

	
	
	
	

	25/6
	Move AT3-DF-A1
	
	Mechanical group

	
	Change AT3-DF ROC (afternoon)
	Leveque
	

	
	PRIMET AT3 test on M2-RR (day)
	Leveque
	

	
	
	
	

	
	Move AT4-DF-G2
	
	Mechanical group

	
	Change AT4-DF ROC 
	Leveque
	

	
	Derotator test (standalone day-time)
	Woillez
	

	
	
	
	

	
	DDL1&3  laser replacement day 2
	Leveque
	TBC

	
	
	
	

	26/6
	DDL1&3  laser replacement day 3
	Leveque
	TBC

	
	Departure S.Leveque
	
	

	
	
	
	


5 Availability

	Jun-13
	Tue
	Wed
	Thu
	Fri
	Sat
	Sun
	Mon
	Tue
	Wed
	Thu
	Fri
	Sat
	Sun
	Mon

	 
	18
	19
	20
	21
	22
	23
	24
	25
	26
	27
	28
	29
	30
	1

	Period
	T
	VLTI UT Run
	 
	 
	 
	PRIMA
	 
	 
	 
	 
	 
	 
	 

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Merand
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Brillant
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	 

	Carlier
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Pozzobon
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Palacio
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Schuhler
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Bourget
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Palanca
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Haguenauer
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Gitton
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Alonso
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Valdes
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Segovia
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Guisard
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Blanchard
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Bolados
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	 

	Leveque
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 


6 Task description
	Identification
	PRIMET pupil tracker calibration on Coude RR

	Priority(high,medium,low)
	high

	Duration
	2 days for each AT
(Day-time)

	Responsible
	leveque

	Description
	Calibrate the DL-VCM offset

	Prerequisite/Predecessor
	AT3 on A1 (or AT4 on J2)
New AT-STS VCM installed

· AT3-DF-A1-DL6 (ROC 185mm)
· AT4-DF-J2-DL4 (ROC 210mm)
M12-A1-DL6 ( or M12-J2-DL4)

	Input
	

	Output
	Updated value for 

	Criteria for Completion
	Primet operating along whole DL stroke

	Successor
	PRIMET AT test on M2-RR 

	Manpower Required
	Leveque

	Facility /Tooling Required
	Whole VLTI

Access to VLTI lab

(confirm  authorization for accessibility during the UT run)

PC connected to Beam profiler
VLTI start-up

	Sequence /procedure(incl. ref doc)
	“Prima Metrology 10th Technical Report

5/7 to 14/7/2011”,

VLT-TRE-ESO-15730-5381 

section 6.1 6.1: Calibration of the AT output pupil longitudinal position (distATPupFixVCM)


	Identification
	PRIMET Test on M2-RR

	Priority(high,medium,low)
	high

	Duration
	1 day for each AT

(Day-time)

	Responsible
	leveque

	Description
	Check the functionality of PRIMET on the M2-RR

	Prerequisite/Predecessor
	· PRIMET pupil tracker calibration on Coude RR
· M2-RR installed

· RR-cover installed (bloc coude RR)



	Input
	-

	Output
	Results of PRIMET health check scripts. 

	Criteria for Completion
	Primet functional on M2-RR

	Successor
	PRIMA sky tests 

	Manpower Required
	Leveque

	Facility /Tooling Required
	Whole VLTI

VLTI start-up

	Sequence /procedure(incl. ref doc)
	Run VLTI start-up

Check PRIMET pupil tracking

Run PRIMET Health check scripts.



	Identification
	DDL laser replacement

	Priority(high,medium,low)
	high

	Duration
	3 days (TBC)

	Responsible
	Leveque 

	Description
	Replace the laser for DDL1-3

	Prerequisite/Predecessor
	Laser available at Paranal



	Input
	-

	Output
	DDL1-3 online 

	Criteria for Completion
	DDL1-3 operates along full stroke
(health check scripts, TBC)

	Successor
	-

	Manpower Required
	Leveque

Paranal support (TBD ??)

	Facility /Tooling Required
	VLTI lab during day-time

Check authorization for accessibility during the UT run

	Sequence /procedure(incl. ref doc)
	TBC by F.Derie.


























































































































































































































































































































































































